## Project Plan
Project Plan
LCR Roles and Responsibilities 2023 Jan-June
Person Responsible
Item # | Status | Date | P. Kelly | Tony | Dawn | Other (Name) | Topic | Detail
1 | Complete | 12/16-12/20/22 | X |  |  |  | PK Contract | Pastor Kelly Vacation (5 days)
2 | Not Started | 2023-12-22 |  | X |  |  | PK Contract | Notify Synod of Last day of PK Contract and Janice start date
3 | Not Started | 2022-12-27 |  | X | X |  | Pastoral Care and funerals | Contract completed for Janice
4 | WIP | ??? | X | X |  |  | PK Contract | Letter to be mailed to the Congregation
5 | Not Started | 2022-12-31 |  | X | X |  | Pastoral Care and funerals | Meet with Janice to confirm contract and start date. Align on 1 schedule for 1/month worship/preaching
6 | Not Started | 2022-12-31 |  | X | X | Cheryl | Staff | Meet with Cheryl: Discuss salary, working in office (Pastor Kelly not planning to be in the office in January) and other items
7 | Not Started | 2022-12-31 |  | X | X | Glen | Staff | Meet with Glen: Discuss salary, working in office (Pastor Kelly not planning to be in the office in January) and other items
8 | Not Started | 2022-12-31 |  | X | X | Rebecca | Staff | Meet with Rebecca: Discuss salary, working in office (Pastor Kelly not planning to be in the office in January) and other items
9 | WIP | 2023-01-01 | X |  |  |  | Worship | Prepare and lead/preach for worship (one service Sunday 9:30 a.m.)
10 | WIP | 2023-01-04 | X |  |  |  | Confirmation | Lead Confirmation
11 | WIP | 2023-01-08 | X |  |  |  | Worship | Prepare and lead/preach for worship (8 a.m. and 10 a.m.)
12 | WIP | 2023-01-08 | X |  |  |  | Youth Night | Lead Youth Night
13 | Not Started | 2023-01-09 | X | X | X | Cheryl - Bulletin | Worship | Must decide how Lent will work this year. Could partner with MPLC. Maybe LCR takes noon on Wed and MPLC takes evenings? Communication needs to be in all bulletins
14 | Not Started | 2023-01-09 |  |  |  | Janice | Pastoral Care and funerals | Janice first day
15 | Not Started | 2023-01-09 |  | X | X |  | S/T Youth Leader Position | Need decision on hiring for 2/1/23-6/1/23 (or include mission trip?) OR Variety of volunteers to manage children's and youth ministry from 1/19-5/28/23
16 | Not Started | 2023-01-09 | X | X | X |  | S/T Youth Leader Position | Posting for job. Applications accepted until 1/13/23. Where will this be posted?
17 | WIP | 2023-01-11 |  |  |  | MPLC | Confirmation | MPLC will lead Confirmation (Pastor Kelly is not available)
18 | Not Started | 1/9-1/13/23 | X |  |  | Janice | Pastoral Care and funerals | Introductions for Janice to visitations/shut-ins, etc.
19 | Not Started | 1/9-1/13/23 | X |  |  |  | Sunday School | Coordinate Sunday School leaders and curriculum for Sundays 1/8-2/19
20 | Not Started | 1/9-1/13/23 | X |  |  |  | S/T Youth Leader Position | Pastor Kelly will prepare training binder
21 | Not Started | 1/9-1/13/23 | X |  |  |  | Youth Night | Pastor Kelly will prepare youth schedule for families and curriculum for Part-time Youth Leader through 2/19/23
22 | Not Started | 2023-01-14 | X | X | X | Rachel, Connie | S/T Youth Leader Position | Job description completed
23 | Not Started | 2023-01-15 | X |  |  |  | Worship | Last of Sunday preaching at LCR (8 a.m. and 10 a.m.)
24 | Not Started | 2023-01-15 | X |  |  |  | Youth Night | Lead Youth Night
25 | Not Started | 1/16-1/18/23 | X | X |  | Rachel, Connie | S/T Youth Leader Position | Interviews completed and job offer made
26 | Not Started | 2023-01-18 | X |  |  |  | Confirmation | Last day of Pastor to Lead Confirmation (at MPLC)
27 | Not Started | 2023-01-18 | X |  |  |  | Adult Ministry | Meet with Brown Bag Book Club
28 | Not Started | 2023-01-22 |  |  |  | Supply Pastor | Worship | Lead/Preach (8 a.m. and 10 a.m.) - Pastor Kelly will schedule
29 | Not Started | 2023-01-22 |  |  |  | PBA Manages (who is this?) | Youth Night | Tubing at Franklin. Pastor Kelly is not available
30 | Not Started | 2022-01-23 |  | X |  | S/T Youth Leader | S/T Youth Leader Position | Start date for some hours beginning 1/23/23 to provide training with Pastor Kelly
31 | Not Started | 1/9-1/27/23 | X |  |  | Cheryl | Worship | Plan supply preachers and bulletins through 2/19/23 (include information on up-coming Annual Meeting in the Bulletins)
32 | Not Started | 1/9-1/27/23 | X |  |  |  | Confirmation | Prepare Confirmation schedule for families and curriculum for leader through 2/25/23
33 | Not Started | 1/9-1/27/23 | X |  |  |  | Sunday School | Purchase Sunday School Curriculum and schedule volunteers for Lent Sundays (2/26-4/2/23) What is last day of Sunday School? Is more curriculum needed?
34 | Not Started | 1/9-1/27/23 | X |  |  |  | RIC | Support Reconciling in Christ team in preparation of the Annual meeting (as needed)
35 | Not Started | 1/9-1/27/23 | X |  |  | Worship Committee | Worship | Working with Worship Committee, prepare Lent plans through Easter Sunday. Does this include working with Musicians?
36 | Not Started | 1/9-1/27/23 | X |  |  | Cheryl | Staff | Oversight and support of creation of the 2022 Annual Report
37 | Not Started | 1/19-1/27/23 | X |  |  | S/T Youth Leader | S/T Youth Leader Position | Training
38 | Not Started | 1/19-1/27/23 | X |  |  | S/T Youth Leader | Youth Night | Create plans for Youth Night going forward (Pastor Kelly will have the plans through 2/19/23 completed
39 | Not Started | 1/19-1/27/23 | X |  |  | Cheryl | Worship | Create Bulletins and work with Musicians to plan worship through 2/19/23
40 | Not Started | 1/19-1/27/23 |  | X | X |  | Annual Meeting | Prepare for Annual Meeting
41 | Not Started | 2023-01-25 |  |  |  | MPLC | Confirmation | Confirmation at MPLC (lead by MPLC) and on-going from this point. Until Confirmation on 5/21/23. Will Connie continue to attend?
42 | Not Started | 2023-01-29 |  |  |  | Rev Kristin Nielsen | Worship | Lead/Preach (8 a.m. and 10 a.m.)
43 | Not Started | 2023-01-29 |  | X | X |  | Annual Meeting
44 | Not Started | 2023-01-29 |  |  |  | S/T Youth Leader | Youth Night | 1:30-3:00 p.m. meeting on Quake at MPLC. Short-term Youth Leader leads first Youth Night and all on-going from this point. Until last night 5/21/23
45 | Not Started | 12/27-12/30/22 | X |  |  |  | Contract | Pastor Kelly Vacation (4 days)
46 | Not Started | 2023-01-31 | X |  |  |  | Contract | Last day of Pastoral Contract at LCR
47 | Not Started | 2023-02-01 |  |  |  | MPLC | Confirmation | Pastor Sheila will lead at MPLC.
48 | Not Started | 2023-02-01 |  | X |  |  | P/T Interim Pastor | Secure a P/T Interim Pastor to start 2/1/23
49 | Not Started | 2/1-on-going |  |  |  | P/T Interim, Janice | Worship | Prepare bulletins and work with Musicians to plan worship on-going
50 | Not Started | 2023-02-05 |  |  |  | Supply Pastor | Worship | Lead/Preach (8 a.m. and 10 a.m.) - Pastor Kelly will schedule
51 | Not Started | 2023-02-05 |  |  |  | S/T Youth Leader | Youth Night | Lead Youth Night
52 | Not Started | 2023-02-08 |  |  |  | MPLC | Confirmation | Pastor Sheila will lead at MPLC.
53 | Not Started | 2/10-2/12/23 |  | X |  | S/T Youth Leader if possible | Youth | Dells Trip: There are enough adults attending that if the S/T Youth Leader can not attend it will be fine. Good if they could attend.
54 | Not Started | 2023-02-12 |  |  |  | Supply Pastor | Worship | Lead/Preach (8 a.m. and 10 a.m.) - Pastor Kelly will schedule
55 | Not Started | 2023-02-12 |  |  |  |  | Youth Night | No Youth Night
56 | Not Started | 2/13-2/15/23 |  |  |  | S/T Youth Leader | Youth Night | Plan and finalize Bowling Event for 3/12/23
57 | Not Started | 2023-02-15 |  |  |  | MPLC | Confirmation | Pastor Sheila will lead at MPLC.
58 | Not Started | 2023-02-19 |  |  |  | Supply Pastor | Worship | Lead/Preach (8 a.m. and 10 a.m.) - Pastor Kelly will schedule
59 | Not Started | 2023-02-19 |  |  |  | S/T Youth Leader | Youth Night | PBA leads at MPLC
60 | Not Started | 2023-02-22 |  |  |  | MPLC | Confirmation | Ash Wednesday - No Confirmation until next year
61 | Not Started | 2023-02-26 |  |  |  | P/T Interim Pastor, Janice | Worship | Lead Worship on-going (with Janice preaching 1 time per month)
62 | Not Started | 2023-02-26 |  |  |  | S/T Youth Leader | Youth Night
63 | Not Started | 2023-03-12 |  |  |  | S/T Youth Leader | Youth Night | Bowling
64 | Not Started | 3/20-4/15/23 |  |  |  | S/T Youth Leader | Youth Night | Plan Year End Celebration for 5/21/23
65 | Not Started | 2023-04-23 |  |  |  | S/T Youth Leader | Mission Trip | Meeting with MPLC (at LCR). What time?
66 | Not Started | 2023-04-01 |  | X | X |  | Permanent Youth Leader | Start have discussions with MPLC to see if what they are looking for in a Youth Leader could be shared with LCR (making it a F/T position?) Need to have this worked out by 5/1/23
67 | Not Started | 2023-05-06 |  |  |  | P/T Interim Pastor, Janice | Wedding | Saturday wedding is scheduled What Time?
68 | Not Started | 2023-05-21 |  |  |  | P/T Interim Pastor | Confirmation | Confirmation (Layla)
69 | Not Started | 2023-05-23 |  |  |  | S/T Youth Leader | Youth Night | Year End Celebration
70 | Not Started | 2023-05-23 |  |  |  | ???? | Senior Sunday | What is this????
71 | Not Started | 2023-06-01 |  | X | X |  | Permanent Youth Leader | Need to start interviewing for this position. Must start no later than 8/1/23 so they have time to on-board and plan. This could result in a shared F/T position or ???

## Look Up (hidden)
Complete
Not Started
WIP