## Sheet1
Team: |  | #1 Building Culture |  |  | Team Names: | Dawn Jacobson, Steve Dues, Tony Baumgardt, Cheryl Cieczka
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
| #1-Culture | 1 |  | Small Cards available for all. Need to continue make them available | Dawn, Cheryl | 2022-11-20 | 2023-06-01
| #1-Culture | 2 |  | Laminated sheets for Council and all committee meetings | Dawn, Cheryl | 2023-01-02 | 2023-06-01 |  |  | Do we need this with the small cards?
|  | 3 |  | Change ending of worship service....."loving Jesus, ....." |  | 2023-02-01 | 2023-03-01
| #1-Culture | 4 |  | 2 month focus on each priority: |  | 2023-01-15 | 2024-06-01
| #1-Culture |  | a | 2 Sermons on the Visioning #1: Building Culture (focus for March/April 2023) |  | 2023-01-15 | 2023-04-01
|  |  | b | Create theme for this series |  | 2023-01-15 | 2023-01-30
|  |  | c | Create new Wifi guest password to tie to theme |  | 2023-01-15 | 2023-01-30
|  |  | d | Create signs to tie to theme |  | 2023-01-15 | 2023-01-30
|  |  | e | Deliver the sermons |  | 2023-03-01 | 2023-04-01
|  |  | f | 2 Sermons on the Visioning #2: Facility/Grounds Usage |  | 2023-03-15 | 2023-06-01
|  |  | g | Create theme for this series |  | 2023-03-15 | 2023-03-30
|  |  | h | Create new Wifi guest password to tie to theme |  | 2023-03-15 | 2023-03-30
|  |  | i | Create signs to tie to theme |  | 2023-03-15 | 2023-03-30
|  |  | j | Deliver the sermons |  | 2023-05-01 | 2023-06-01
|  |  | k | 2 Sermons on the Visioning #3: Youth Innovation |  | 2023-08-15 | 2023-11-01
|  |  | l | Create theme for this series |  | 2023-08-15 | 2023-08-30
|  |  | m | Create new Wifi guest password to tie to theme |  | 2023-08-15 | 2023-08-30
|  |  | n | Create signs to tie to theme |  | 2023-08-15 | 2023-08-30
|  |  | o | Deliver the sermons |  | 2023-10-01 | 2023-11-01
|  |  | h | 2 Sermons on the Visioning #4: Adult Relationships |  | 2024-01-15 | 2024-04-01
|  |  | i | Create theme for this series |  | 2024-01-15 | 2024-01-30
|  |  | j | Create new Wifi guest password to tie to theme |  | 2024-01-15 | 2024-01-30
|  |  | k | Create signs to tie to theme |  | 2024-01-15 | 2024-01-30
|  |  | l | Deliver the sermons |  | 2024-03-01 | 2024-04-01
|  |  | m | 2 Sermons on the Visioning #5: Member Engagement |  | 2024-03-15 | 2024-06-01
|  |  | n | Create theme for this series |  | 2024-03-15 | 2024-03-30
|  |  | o | Create new Wifi guest password to tie to theme |  | 2024-03-15 | 2024-03-30
|  |  | p | Create signs to tie to theme |  | 2024-03-15 | 2024-03-30
|  |  | q | Deliver the sermons |  | 2024-05-01 | 2024-06-01
|  | 5 |  | Final wifi guest password....incompass our overall vision..... |  | 5/15/0204 | 2024-06-01 |  |  | This is on-going
|  | 6 |  | Monitor and track measures for this strategy
|  |  | a | Council Meetings have integrated all priorities into discussion and all decisions. Achieve 100% consistency for 3 consecutive months by 6/1/2023 Measure by Secretary each meeting (include results in Council meeting minutes) |  | 2023-02-01 | 2023-06-01
|  |  | b | Committee come to Council for approval with Priority that matchs recommendation Achieve 100% conssistency for 3 consecutive months by 12/1/2023 Measure by Secretary each meeting (include results in Council meeting minutes) |  | 2023-02-01 | 2023-12-01
|  |  | c | Congregation knows the priorities and uses them with recommendations proposed Achieve 100% consistency for 3 consecutive months by 6/1/2024 Measure by Executive Committee and Pastor with all proposals (include results in Council meeting minutes) |  | 2023-02-01 | 2024-06-01