## Sheet1
Project Plan
LCR Roles and Responsibilities for Bridge Transition Time
Person Responsible
Bridge Item # | Sub Item # | Bridge Status | P. Kelly | Tony | Dawn | Other (Name) |  | Tasks | After Bridge: Ideas/thoughts
1 |  | Open Item | X | X | X |  | Align on Timing of Bridge Responsibilities
Needs to be discussed
2 |  |  | X |  |  |  | Performing Worship and Special Services (Weddings/Funerals/Baptisms) |  | For longer term, may want to consider someone (Deacon, or Pastor, or Lay person) for 10-15 hours per week to do visitations, preaching, prime timers, etc.
| 2a | Complete | X |  |  |  |  | P. Kelly will perform these duties. Will need a Supply Pastor to cover 1 Sunday/month, scheduled vacations, and business trips
| 2b | Not Started | X |  |  |  |  | Need to secure a "Supply" Pastor for 1 Sunday per month and to cover Pastor Kelly vacations. Need this after summer. | Need to develop an AV team to support Live Stream at 8 a.m. service and Sound and Live Stream at 10 a.m. service.
3 | [6 empty] | Staff Supervision
| 3a | Complete |  | X |  |  |  | Tony to discuss with Cheryl that she will take on the responsibilities for supervision of Glen, Rebecca, and Glen's backup
| 3b | Not Started |  | X |  |  |  | Need to determine a back up for Glen for vacations, etc. Need a list of critical items.
| 3c | Complete | X |  |  |  |  | P. Kelly will manage the Staff Meetings (primarily focused on Sunday Services) and Music Staff (Lynette and Jim)
| 3d | WIP |  | X |  |  |  | UPDATE: Dawn will supervise Cheryl. Tony to talk with Cheryl about this and any other communication needed. | Need to determine a back up plan for Cheryl. Dawn/Finance Committee will work on this proposal
4 |  | Complete |  |  |  | Stacy Robe | Worship Committee
[8 empty] | This committee focuses on volunteers. No changes needed as Stacy Robe manages this well. | Consider moving this committee to take on more of a leadership role for Services?
5 | [6 empty] | Building and Grounds Committee This includes: Flower Beds, Cutting grass volunteers, parking lot, snow shoveling/plowing, emergencies, etc.
| 5a | Complete |  | X |  |  |  | Tony will ask John Mantey (given his strong knowledge of the building, etc.) with guiding Glen on things needing to be done as well as be a contact for emergencies, etc. John Mantey agreed to this.
| 5b | Complete |  | X |  |  |  | Tony will discuss with Jon Wint and John Cline about John Mantey helping out. Also that communication for emergency and non-emergency items should go to "the 3 Johns" with a cc to both Tony and Dawn
6 | [6 empty] | Visioning Committee and Pastor Holm's Cohort
| 6a | Complete | X |  |  |  |  | P. Kelly will lead visioning through Sept. This will include taking the role on the visioning "cohort" team of Pastors in August with P. Holm.
| 6b | Complete | X |  |  |  |  | P. Kelly to discuss with Steve Jacobson his attending August Cohort meeting. Steve might get to ask his question then. Pastor Holm said Steve could not attend.
|  | Complete | X |  |  |  |  | P. Kelly to discuss with P. Holm if Dawn and Steve Jacobson can attend another visioning group session since they can not attend the Sept one. Pastor Holm said no to this option.
| 6c | Complete | X | X | X |  |  | Need to determine a Visioning and Cohort lead going forward (after Sept). Per Pastor Holm, this should be Pastor Kelly
7 | [6 empty] | Stewardship Committee
| 7a | Complete |  | X |  |  |  | Tony will discuss with Harold Holm about helping with Stewardship. Harold agreed
| 7b | Complete |  |  | X | John Mantey |  | Dawn will set up a meeting with John Mantey, Harold Holm, and herself to discuss initial plans for Stewardship, getting others involved, and need for communication to P. Kelly before end of August (Worship dates/content). UPDATE: Meeting completed on 7/26/22. John will lead from this point going forward
| 7c | Complete |  |  | X |  |  | Dawn will discuss with Cheryl what she did for Stewardship last year. UPDATE: Requested from Cheryl, she will complete after her vacation.
8 | [6 empty] | Adult Education Committee
| 7a | Complete | [5 empty] | Agreed to not work on the Convesation Café's during the Bridge period
| 7c | Complete |  | X |  |  |  | Tony to ask Mary Hauch to coordinate the Book Club, Bible Study, Prime Timer's and Circles. Mary agreed to this. Pastor will attend any when asked.
9 |  | Complete |  |  |  | Sandy G. | Visitations
Sandy Georgeson is leading the "LCR Angels". Leave as is
10 |  | Complete |  |  |  |  | New Member process |  | Develop New Member process by January. Only members can vote (don't currently track when voting), Consitution says communion within 1 year and contribution ($ or time?), need to identify new givers - Dawn can do this.
Agreed will work on a new process in January
11 |  | WIP |  | X |  |  | Fellowship Committee
Tony will ask Dave Backmann to lead. Tailgate Worship on 10/8/22 (Sat with Cookout after)
12 |  | Complete |  |  |  |  | Community Outreach Committee
This includes Community Meals/Hospitality Center and Neighborhood Camp
Tony will as Cara/Jeff Wunderle to lead. Jeff agreed
13 | [6 empty] | Other:
| 13a | Complete |  |  | X |  |  | Dawn to insure P. Karen's Credit Card was turned in. Dawn confirmed it was. Card is still in service for now until some automatic charges can be changed to another card. | Finance Committee to review Credit Cards longer term. Credit Card limit for Pastor Kelly needs to be increased and automatic payments needs to be moved from Pastor Karen's Card to Pastor Kelly's Card and then Pastor Kelly's card to be cancelled. This is WIP at this time.
| 13b | WIP |  | X | X |  |  | Need a policy on who needs to approve spending and what levels. Resurrect and update the document that was started earlier. Need by August?
|  | WIP |  | X |  |  |  | Set up next meeting (P. Kelly, Tony, Dawn) before September 19th Council meeting to understand what is working and not working.
|  | WIP | X | X | X |  |  | No changes are needed yet to the Call Document for P. Kelly but a new job description and $ will needed by end of August for Council Approval in September
| 13c | WIP |  | X |  |  |  | Tony to consider communication plan - DONE * Sunday communication to congregation - DONE * Letter to the congregation? DONE * Email to Committee Leads DONE * Once we have a signed Bridge contract with Pastor Kelly, need to communicate to Congregation
14 |  | WIP |  |  |  |  | Youth Committee
[5 empty] | X |  |  | Dawn to continue work on policy for funds for Youth/Scrip….Consider Mission trip funds and Youth. Consider if Parship Ed is combined. Draft completed and under review by committee. | Consider combining Parish Ed (Sunday School, Confirmation, Cradle Roll, and Library) with Youth Committee.
15 |  | WIP |  |  |  |  | Membership Committee
[5 empty] | X |  |  | Dawn will work with Cheryl to develop recommendation for "cleaning up" membership. Recommendation will need to go to council before changes can be made. Cheryl has done a lot of work on this. Dawn is currently reviewing. Concern to consider those who are returning in the next few months. Approved by Tony to remove specific folks that have passed away or moved out of the area and no longer give.