## Sheet1
Project Plan: Sanctuary Stage and Carpet
Core Team
# | Timing | Dependencies |  | Cost Estimate | Status | Glenn H. | Chris (or Jon) | Mary H | John A | Ryan G | Dawn | Other(s) |  | Tasks | Additional Comments
|  | Before | After |  |  | Lead is bold X (x for helpers)
1 |  |  |  | 0 | Complete |  | X | [5 empty] | Electrical & HVAC
1a | 2025-08-17 |  |  |  | Complete |  | X | [6 empty] | Review completed and confirmed no major Electrical or HVAC concerns
2 |  |  |  | 11000 | [8 empty] | Proposal
2a | 2025-08-24 |  |  |  | Complete | x | x | x | x | x | X |  |  | Develop Project Plan
2b | 2025-09-05 |  |  | 1000 | [6 empty] | X |  |  | Add 10% contingency
2c | 2025-08-25 |  |  |  | Delete |  |  |  | x |  | X |  |  | Get name of John's stage builder (needs to go to Chris)
2d | 2025-08-25 |  |  |  | Delete |  |  |  | x |  | X |  |  | Distribute stage specs (needed all core team)
2e | 2025-09-25 |  |  |  | NEW | x | x | x | x | x | X |  |  | Find a contractor for the stage build and develop specs
2f |  |  | Multi |  | WIP | x | x | x | x | x | X |  |  | Complete all estimates and final specs/design
2g | [5 empty] | x | x |  |  |  | X |  |  | Jon W update and approval to move forward
2h | [10 empty] | X |  |  | Secure approval from Finance Committee
2i | [5 empty] | x | x | x | x | x | x | X Jon |  | Secure approval from Council
2j | on-going | [9 empty] | X |  |  | Manage/update/communicate project plan through completion
3 |  |  |  | 0 | [8 empty] | Brick pulpit/wall removal |  | Per Glen no permit is needed
3a | [5 empty] | x |  |  |  |  | X |  |  | Send out "inform" to Council (or cover during Council project approval depending on timing of brick removal)
3b | [5 empty] | X | [7 empty] | Determine timing based on Stage Installation date
3c | [5 empty] | X |  |  | x |  |  | Lynette |  | Remove any needed band equipment for brick removal (any cabling disconnection needed?) - Glenn will determine if any equipment needs to be moved and communicate to John/Lynette
3d | [5 empty] | X |  |  | x | x |  |  |  | Glenn will lead and get volunteer support (John and Ryan will help)
3e | [5 empty] | X |  |  | x |  |  | Lynette |  | Replace any moved band equipment (cabling reconnected if needed)
4 |  |  |  | 0 | [8 empty] | Align with Band on Stage design/specs and timing
4a | [5 empty] | X | [5 empty] | Lynette, Fred |  | Meeting to align on Specs/timing of band equip move/cabling needs (this should include stage layout for equipment, how many and where the "cable trap doors" will be placed, etc)
4b | [5 empty] | X | [7 empty] | Communicate to core team the decision on best way to hid cables, placement of "cable trap doors" and final stage layout plan
5 | [12 empty] | Stage Installation
5a |  | 5d |  |  |  |  | X |  | x |  |  |  |  | Secure builder: timing and cost (including installation & cabling decision) - understand if permit is needed (may change our timing?)
5b | [6 empty] | x |  | X |  |  | All Band? |  | Remove band equipment and disconnect cabling
5c |  | 5d |  |  |  |  | X | [6 empty] | Install stage
5d |  | 2f |  |  |  |  | x |  | X |  |  | All Band? |  | Replace all band equipment and cabling reconnected
6 | [12 empty] | Carpet Installation
6a | 2025-08-21 |  |  |  | Complete |  |  | X | x | x |  |  |  | John, Ryan, and Mary to meet on 8/21
6b | 2025-09-01 |  |  |  | Complete |  |  | X | [5 empty] | Cost quotes for commercial grade carpet
6c |  | 2f |  | 10000 | WIP |  |  | X | x | x |  |  |  | Select vendor and align on cost and timing
6d | [7 empty] | X |  |  |  | Worship? |  | What prep is needed for the installation?
6e |  |  | 2j |  |  |  |  | X | [5 empty] | Install Carpet
6f | [7 empty] | X |  |  |  | Worship? |  | Prep for worship
7 |  |  |  | 0 | [8 empty] | Install Shiplap (with short lip) and window bar(s)
7a | [5 empty] | X | [7 empty] | Install shiplap (includes getting materials, etc)
7b | [5 empty] | X | [7 empty] | Install window bar(s) (includes materials and making as needed)