## Team #1
Team: |  | #1 Building Culture |  |  | Team Names: | Dawn Jacobson, Steve Dues, Tony Baumgardt, Cheryl Cieczka
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
WIP | #1-Culture | 1 |  | Small Cards available for all. Need to continue make them available | Dawn, Cheryl | 2022-11-20 | 2023-06-01
| #1-Culture | 2 |  | Laminated sheets for Council and all committee meetings | Dawn, Cheryl | 2023-01-02 | 2023-06-01 |  |  | Do we need this with the small cards?
|  | 3 |  | Change ending of worship service....."loving Jesus, ....." |  | 2023-02-01 | 2023-03-01
|  | 4 |  | Consider engaging a strong marketing firm to help us. |  | 2023-01-15 | 2023-03-01
|  | 5 |  | Consider purchase of electronic sign for front |  | 2023-01-15 | 2023-03-01
|  |  | a | Price costs |  | 2023-01-15 | 2023-01-30
|  |  | b | Prepare for presentation to Council |  | 2023-02-01 | 2023-02-10
|  |  | c | Present to Council for approval |  | 2023-02-20 | 2023-02-20
|  |  | d | Schedule and install sign |  | 2023-03-01 | 2023-03-01
|  |  | e | Train on how to manage signage |  | 2023-03-01 | 2023-03-15
| #1-Culture | 6 |  | 2 month focus on each priority: |  | 2023-01-15 | 2024-06-01
| #1-Culture |  | a | 2 Sermons on the Visioning #1: Building Culture (focus for March/April 2023) |  | 2023-01-15 | 2023-04-01
|  |  | b | Create theme for this series |  | 2023-01-15 | 2023-01-30
|  |  | c | Change electronic signage (if available) |  | 2023-01-15 | 2023-01-30
|  |  | d | Create signs to tie to theme |  | 2023-01-15 | 2023-01-30
|  |  | e | Deliver the sermons |  | 2023-03-01 | 2023-04-01
|  |  | f | 2 Sermons on the Visioning #2: Facility/Grounds Usage |  | 2023-03-15 | 2023-06-01
|  |  | g | Create theme for this series |  | 2023-03-15 | 2023-03-30
|  |  | h | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2023-03-15 | 2023-03-30
|  |  | i | Create signs to tie to theme |  | 2023-03-15 | 2023-03-30
|  |  | j | Deliver the sermons |  | 2023-05-01 | 2023-06-01
|  |  | k | 2 Sermons on the Visioning #3: Youth Innovation |  | 2023-08-15 | 2023-11-01
|  |  | l | Create theme for this series |  | 2023-08-15 | 2023-08-30
|  |  | m | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2023-08-15 | 2023-08-30
|  |  | n | Create signs to tie to theme |  | 2023-08-15 | 2023-08-30
|  |  | o | Deliver the sermons |  | 2023-10-01 | 2023-11-01
|  |  | h | 2 Sermons on the Visioning #4: Adult Relationships |  | 2024-01-15 | 2024-04-01
|  |  | i | Create theme for this series |  | 2024-01-15 | 2024-01-30
|  |  | j | Change electronic signage (if available) |  | 2024-01-15 | 2024-01-30
|  |  | k | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2024-01-15 | 2024-01-30
|  |  | l | Deliver the sermons |  | 2024-03-01 | 2024-04-01
|  |  | m | 2 Sermons on the Visioning #5: Member Engagement |  | 2024-03-15 | 2024-06-01
|  |  | n | Create theme for this series |  | 2024-03-15 | 2024-03-30
|  |  | o | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2024-03-15 | 2024-03-30
|  |  | p | Create signs to tie to theme |  | 2024-03-15 | 2024-03-30
|  |  | q | Deliver the sermons |  | 2024-05-01 | 2024-06-01
|  | 7 |  | Monitor and track measures for this strategy
|  |  | a | Council Meetings have integrated all priorities into discussion and all decisions. Achieve 100% consistency for 3 consecutive months by 6/1/2023 Measure by Secretary each meeting (include results in Council meeting minutes) |  | 2023-02-01 | 2023-06-01
|  |  | b | Committee come to Council for approval with Priority that matchs recommendation Achieve 100% conssistency for 3 consecutive months by 12/1/2023 Measure by Secretary each meeting (include results in Council meeting minutes) |  | 2023-02-01 | 2023-12-01
|  |  | c | Congregation knows the priorities and uses them with recommendations proposed Achieve 100% consistency for 3 consecutive months by 6/1/2024 Measure by Executive Committee and Pastor with all proposals (include results in Council meeting minutes) |  | 2023-02-01 | 2024-06-01

## 2023 Capacity Review
LCR Strategy Capacity Review
Completed 1/7/2023 at Visioning Meeting with Pastor Holm
Color Key: Green = Do first, Yellow = do if time permits
Priority | Build Culture | Facility Use | Young People | Adult Relationships | Community Service | MET Team | Call Committee
2023 Tasks | Thematic Worship Planning | Facility Evaluation | Temporary Youth Coordinator | Evaluate Current Programs | Identify what we do now | Complete MET Process | Complete Call Process
| Marketing: Foundational Doc | Facility Specs/Availability | Explore Partnerships | Quarterly Event Research | Identify Members Skills
| Intentional Storytelling | Reach out to ???????? | Sunday School Reboot | Quarterly Event Planning | Connections Coordinator
|  | Publicity | Communication Technology | RIC Process | Make Serving Ops Missional
|  | Grants for Facility Updates | Explore Daycare |  | Explore Partnerships
|  |  | RIC Process - up & running |  | Identify Community Needs
People Resources | Current Committee | Current Committee | Current Committee | Current Committee | Current Committee | 5-6 People | 7 People
| Cheryl's Time | Cheryl's Time | Youth Coordinator | Fellowship Committee |  | 3 month
| Communications Expert | Buildings & Grounds | 10-13 Volunteers
Security Expansion/Admin
$ Resources (costs) | 1000 | $ TBD | 1500 | 500 | 500 | None expected | $ Funded
Youth Coordinator and SS Curriculum are funded in budget

## Potential Issues
|  | Tactical | Strategic | Adaptive | Notes
1 | Building Culture |  |  | People will resist to using the structure Currently some activities we do don't fit into this | Tell stories of the impact of our ministries!

## Data (hidden)
Drop Down List
Completed | #1-Build Culture | #1 Building Culture
Not Started | #2-Facility/Grounds | #2 Facility/Grounds Usage
WIP | #3-Youth | #3 Youth Innovation
| #4-Adults | #4 Adult Relationships
| #5-Engagement | #5 Member Engagement