## Instructions
Welcome to our Visioning Project Plan!
Click on your team tab (below) and use that sheet to upate your project plan.
Update your project plan.
Please do not add/delete columns as we need to combine all the sheets in the future.
Need help: Contact Dawn Jacobson dmj7140@gmail.com or 262-902-3373

## 2023 Capacity Review
LCR Strategy Capacity Review
Completed 1/7/2023 at Visioning Meeting with Pastor Holm
Color Key: Green = Do first, Yellow = do if time permits
Priority | Build Culture | Facility Use | Young People | Adult Relationships | Community Service | MET Team | Call Committee
2023 Tasks | Thematic Worship Planning | Facility Evaluation | Temporary Youth Coordinator | Evaluate Current Programs | Identify what we do now | Complete MET Process | Complete Call Process
| Marketing: Foundational Doc | Facility Specs/Availability | Explore Partnerships | Quarterly Event Research | Identify Members Skills
| Intentional Storytelling | Reach out to ???????? | Sunday School Reboot | Quarterly Event Planning | Connections Coordinator
|  | Publicity | Communication Technology | RIC Process | Make Serving Ops Missional
|  | Grants for Facility Updates | Explore Daycare |  | Explore Partnerships
|  |  | RIC Process - up & running |  | Identify Community Needs
People Resources | Current Committee | Current Committee | Current Committee | Current Committee | Current Committee | 5-6 People | 7 People
| Cheryl's Time | Cheryl's Time | Youth Coordinator | Fellowship Committee |  | 3 month
| Communications Expert | Buildings & Grounds | 10-13 Volunteers
Security Expansion/Admin
$ Resources (costs) | 1000 | $ TBD | 1500 | 500 | 500 | None expected | $ Funded
Youth Coordinator and SS Curriculum are funded in budget

## Potential Issues
|  | Tactical | Strategic | Adaptive | Notes
1 | Building Culture |  |  | People will resist to using the structure Currently some activities we do don't fit into this | Tell stories of the impact of our ministries!
2 | Facility | How do we tell the congregation that we are doing these extra little things? (ie. How it's on mission) | Security Custodial services Need a consistent usage agreement or revise it | Need to define "purposefully define God's love" Could we be more "on mission"? How to deal with strangers (non-members) in the buildings | "Donation" or usage fee to the church, NOT rent
3 | Youth |  | RIC: what does it mean for how we do ministry? | Critical Mass: 1) how do we get bigger? 2) how do we be successful with fewer? Change culture to say we're fully welcoming/ accepting Communication with youth How do you navigate with rest of church if we change worship (for example) | Innovative = risk-taking. How do we take risks, get kids to know one another, make it a safe place… 2 kinds of social media pages: 1) Static (ie basic info on church and services 2) Interactive (ie. Prayers, events, personal, etc.), members need to join and be approved SS curriculum - Godly Play
4 | Adults |  | --Provide a meal | --Overcoming the busy-ness of people (ie. Overcome interia) --Find activities that interest a variety of people
5 | Engagement |  | What are the various things that we need and then show them that | How do we communicate differently? People feel too busy What value do they see? Maybe we're not doing a mission project we should be doing | Put the person at the center, not the church "Connections coordinator" vs. volunteer coordinator Think broadly to get a variety fo opportunties for people 1 big mission identity (1 thing we're known for), then a few smaller ones

## Team #1
Team: |  | #1 Building Culture |  |  | Team Names: | Dawn Jacobson, Steve Dues, Tony Baumgardt, Cheryl Cieczka
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
WIP | #1-Culture | 1 |  | Small Cards available for all. Need to continue make them available | Dawn, Cheryl | 2022-11-20 | 2023-06-01
| #1-Culture | 2 |  | Laminated sheets for Council and all committee meetings | Dawn, Cheryl | 2023-01-02 | 2023-06-01 |  |  | Do we need this with the small cards?
|  | 3 |  | Change ending of worship service....."loving Jesus, ....." |  | 2023-02-01 | 2023-03-01
|  | 4 |  | Consider engaging a strong marketing firm to help us. |  | 2023-01-15 | 2023-03-01
|  | 5 |  | Consider purchase of electronic sign for front |  | 2023-01-15 | 2023-03-01
|  |  | a | Price costs |  | 2023-01-15 | 2023-01-30
|  |  | b | Prepare for presentation to Council |  | 2023-02-01 | 2023-02-10
|  |  | c | Present to Council for approval |  | 2023-02-20 | 2023-02-20
|  |  | d | Schedule and install sign |  | 2023-03-01 | 2023-03-01
|  |  | e | Train on how to manage signage |  | 2023-03-01 | 2023-03-15
| #1-Culture | 6 |  | 2 month focus on each priority: |  | 2023-01-15 | 2024-06-01
| #1-Culture |  | a | 2 Sermons on the Visioning #1: Building Culture (focus for March/April 2023) |  | 2023-01-15 | 2023-04-01
|  |  | b | Create theme for this series |  | 2023-01-15 | 2023-01-30
|  |  | c | Change electronic signage (if available) |  | 2023-01-15 | 2023-01-30
|  |  | d | Create signs to tie to theme |  | 2023-01-15 | 2023-01-30
|  |  | e | Deliver the sermons |  | 2023-03-01 | 2023-04-01
|  |  | f | 2 Sermons on the Visioning #2: Facility/Grounds Usage |  | 2023-03-15 | 2023-06-01
|  |  | g | Create theme for this series |  | 2023-03-15 | 2023-03-30
|  |  | h | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2023-03-15 | 2023-03-30
|  |  | i | Create signs to tie to theme |  | 2023-03-15 | 2023-03-30
|  |  | j | Deliver the sermons |  | 2023-05-01 | 2023-06-01
|  |  | k | 2 Sermons on the Visioning #3: Youth Innovation |  | 2023-08-15 | 2023-11-01
|  |  | l | Create theme for this series |  | 2023-08-15 | 2023-08-30
|  |  | m | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2023-08-15 | 2023-08-30
|  |  | n | Create signs to tie to theme |  | 2023-08-15 | 2023-08-30
|  |  | o | Deliver the sermons |  | 2023-10-01 | 2023-11-01
|  |  | h | 2 Sermons on the Visioning #4: Adult Relationships |  | 2024-01-15 | 2024-04-01
|  |  | i | Create theme for this series |  | 2024-01-15 | 2024-01-30
|  |  | j | Change electronic signage (if available) |  | 2024-01-15 | 2024-01-30
|  |  | k | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2024-01-15 | 2024-01-30
|  |  | l | Deliver the sermons |  | 2024-03-01 | 2024-04-01
|  |  | m | 2 Sermons on the Visioning #5: Member Engagement |  | 2024-03-15 | 2024-06-01
|  |  | n | Create theme for this series |  | 2024-03-15 | 2024-03-30
|  |  | o | Change electronic signage (if available). Consider rotating with previous priorities. |  | 2024-03-15 | 2024-03-30
|  |  | p | Create signs to tie to theme |  | 2024-03-15 | 2024-03-30
|  |  | q | Deliver the sermons |  | 2024-05-01 | 2024-06-01
|  | 7 |  | Monitor and track measures for this strategy
|  |  | a | Council Meetings have integrated all priorities into discussion and all decisions. Achieve 100% consistency for 3 consecutive months by 6/1/2023 Measure by Secretary each meeting (include results in Council meeting minutes) |  | 2023-02-01 | 2023-06-01
|  |  | b | Committee come to Council for approval with Priority that matchs recommendation Achieve 100% conssistency for 3 consecutive months by 12/1/2023 Measure by Secretary each meeting (include results in Council meeting minutes) |  | 2023-02-01 | 2023-12-01
|  |  | c | Congregation knows the priorities and uses them with recommendations proposed Achieve 100% consistency for 3 consecutive months by 6/1/2024 Measure by Executive Committee and Pastor with all proposals (include results in Council meeting minutes) |  | 2023-02-01 | 2024-06-01

## Team #2
Team: |  | #2 Facility/Grounds Usage |  |  | Team Names: | Dave Backmann, Leah Krueger, Mary Hauch, Terry Backmann, and Lindsay Stolen
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
Completed | #1-Culture | 1 |  | Team Meeting to Review Needs and Timeline | Dave Backmann | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2022-11-30
| #1-Culture | 2 |  | Immediate Attention
| #1-Culture |  | a | Upgrade Bandwidth for internet (Dave will bring to council) |  | 2023-01-15 | 2023-03-31
| #1-Culture |  | b | Complete backlighting for Risen Christ and stone over alter (Mary will contact Bohm Electric) |  | 2023-01-15 | 2023-03-31
|  | 3 |  | Short term needs (two to five years)
|  |  | a | Repair Soffits
|  |  | b | Complete reconstruction of parking lot
|  |  | c | Fix lower level (classrooms) heating regulation (too warm, wasting energy)
|  | 4 |  | Long term needs
|  |  | a | Remodel kitchen to bring up to code (including electrical, drain and grease trap)
|  |  | b | Install Windows to code in lower level classrooms
|  | 5 |  | Potential Use for facility
|  |  | a | Polling Place
|  |  | b | Men's Breakfast
|  |  | c | Musice Lessons: Recitals; Concerts
|  |  | d | After School Program for Goodland
|  |  | e | Yoga Classes (Christian Meditative)
|  |  | f | Children's Story Hour (daytime weekly)
|  |  | g | Non-Profit Meeting Center: SE Wisconsin LGBTQ; AA; Big Sisters of Greater Racine; PEO
|  |  | h | Senior Day Care
|  |  | i | Community Activities: Trunk or Treat; Easter Egg Hunt; Summer Picnic
|  | 6 |  | Long Range Potential (requires facility upgrades)
|  |  | a | Day Care
|  |  | b | Community Meal
|  |  | c | Basketball Hoop and Pickleball Court

## Team #3
Team: |  | #3 Youth Innovation |  |  | Team Names: | Rachel Petrach, Nicci D'Amour, Jennifer Klemick
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
WIP | #1-Culture | 1 |  | Hire youth coordinator
Not Started | #1-Culture | 2 |  | Full SS rooms downstairs
Not Started | #1-Culture | 3 |  | Build a youth community center
Not Started | #1-Culture | 4 |  | Daycare
Not Started |  | 5 |  | Using latest technology to connect with youth

## Team #4
Team: |  | #4 Adult Relationships |  |  | Team Names: | Steve Jacobson, John Mantey, Heather Keszler, Kathy Andreasen, Carl
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
Not Started | #1-Culture | 1 |  | Quarterly Game Night | [5 empty] | Easy to establish fairly quickly
| #1-Culture |  | a | Choose dates and times |  | 2023-02-01 | 2023-11-01
| #1-Culture |  | b | Choose and secure a venue (Twin Dragon Games, Gamstersbay, The Sanctum, church)
| #1-Culture |  | c | Choose a game or games (could also be video games, could then offer online)
|  |  | d | Decide if we will offer food and beverages (will depend on location) | [5 empty] | 300
|  |  | e | Find out if people want/need to carpool: create groups based on need
Not Started |  | 2 |  | Quarterly Event/Outing |  | 2023-02-01 | 2023-12-01 |  |  | Easy to plan fairly quickly
|  |  | a | Choose event: will be dependent on time of year
|  |  | c | Based on type of event, choose date and time
Ex: Feb/March, wine tasting; May/June, baseball game; Sept/Oct, Apple Holler or pumpkin farm; Nov/Dec, theatre or concert
|  |  | b | Look for events that are already happening in our area to make planning easier
|  |  | d | Plan any subsequent needs for each event
Ex. tailgating for baseball game, dinner before a play, etc. (this will be event specific)
|  |  | e | Find out if people want/need to carpool; create groups based on need

## Team #5
Team: |  | #5 Member Engagement |  |  | Team Names: | Connie Gardner, Stacy Robe, Colin McKenna, Linda Lewis
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
WIP | #1-Culture |  |  | Get a list of current community service projects and mission projects
Not Started |  |  | a | Connect with each committee to determine available projects, details of projects, contacts (internal/external), etc.
Not Started
Not Started | #1-Culture |  |  | Get a list of current congregation members
Not Started | #1-Culture |  |  | Discuss hiring a volunteer coordinator (churchwide position)
Not Started | #1-Culture |  |  | Research service needs in the community
Not Started |  |  |  | Create tracking system for volunteers/community services/project engagement
WIP |  |  |  | Get list of current project/volunteer needs within the church

## Sample
Team: |  | #1 Building Culture |  |  | Team Names: | Dawn Jacobson, Steve Dues
Status | Team # | Main Task # | Sub-Task Letter (if main task leave blank) | Task Description (indent 5 spaces for sub-tasks) | Task Lead or Sub-Task Responsible Person | Expected dates |  | Actual |  | Notes
[6 empty] | Start date | Completion date | Start date | Completion date
Completed | #1-Culture | 1 |  | Arrange first meeting | Dawn | 2023-01-01 | 2023-01-01 | 2023-01-01 | 2023-01-01
Completed | #1-Culture | 1 | a | Call all team members for possible dates | Dawn | 2023-01-02 | 2023-01-02 | 2023-01-01 | 2023-01-01
Completed | #1-Culture | 1 | b | Select date/time and location | Tony | 2023-01-03 | 2023-01-03 | 2023-01-01 | 2023-01-01
Completed | #1-Culture | 1 | c | Send email to all team members | Dawn | 2023-01-03 | 2023-01-03 | 2023-01-01 | 2023-01-01
WIP |  | 2 |  | First Meeting Agenda | Dawn | 2023-01-10 | 2023-01-10 | 2023-01-01 | 2023-01-01
WIP |  | 2 | a | Create and Send out first meeting agenda | Dawn
Not Started |  | 2 | b | Send out meeting notes from first meeting agenda | Dawn

## Data (hidden)
Drop Down List
Completed | #1-Build Culture | #1 Building Culture
Not Started | #2-Facility/Grounds | #2 Facility/Grounds Usage
WIP | #3-Youth | #3 Youth Innovation
| #4-Adults | #4 Adult Relationships
| #5-Engagement | #5 Member Engagement