## Sheet1
Part-Time Coordinator of Children's and Youth Ministries
Estimated Hours per month
|  | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
Nursery Coverage:
1 | Volunteers Aligned | [12 empty] | 9 | bar: Jan to May; Sept to Dec
2 | Training Volunteers | Jan: 2; Sept: 2 | 4
Sunday School | [13 empty] | 0
1 | Develop/research, pick and purchase curriculum | July: 5 | 5
2 | Develop training material | Aug: 5 | 5
3 | Volunteers aligned | [12 empty] | 1 | bar: Aug
4 | Train Volunteers | Aug: 2 | 2
5 | Oversight of SS each week and address issues | 4 | 4 | 5 | 4 | 4 |  |  |  | 5 | 4 | 4 | 5 | 39
First Communion | [13 empty] | 0
1 | Develop/research, pick and purchase curriculum | Feb: 5 | 5
2 | Develop training material | Mar: 4 | 4
3 | Volunteers aligned | [12 empty] | 1 | bar: Mar
4 | Train Volunteers | Mar: 2 | 2
5 | Oversight of SS each week and address issues | Mar: 5; April: 4; May: 4 | 13
Confirmation | [13 empty] | 0
1 | Develop/research, pick and purchase curriculum | July: 5 | 5
2 | Develop training material | Aug: 5 | 5
3 | Volunteers aligned | [12 empty] | 1 | bar: Aug
4 | Train Volunteers | Aug: 2 | 2
5 | Oversight of SS each week and address issues | 4 | 4 | 5 | 4 | 4 |  |  |  | 5 | 4 | 4 | 5 | 39
6 | Over night (5 days) - develop plan and coordinate trip | April: 3; May: 3 | 6
7 | Attend Week overnight (5 days) | June: 120
Sunday Night Youth Night | [13 empty] | 0
1 | Develop weekly material, plans, events, etc | 8 | 8 | 8 | 8 | 8 |  |  | 5 | 8 | 8 | 8 | 8 | 77
2 | Attend weekly youth night | 4 | 4 | 5 | 4 | 4 |  |  |  | 5 | 4 | 4 | 5 | 39
Mission Trip | [13 empty] | 0
1 | Plan, select, coordinate, communicate, get needed Adult Leaders, etc | Jan: 4; Feb: 4; Mar: 4; April: 4; May: 4; June: 4; July: 4 | 28
2 | Attend trip | Aug: 168 | 168
Neighborhood Camp | [13 empty] | 0
1 | Coordinate with Camp Community Director | Feb: 2; Mar: 2 | 4
2 | Plan and get volunteers | Mar: 4 | 4
3 | Attend Neighborhood Camp (all day?) | June: 40; July: 160 | 200
Other
1 | Plan and action fundraisers | Jan: 4; Mar: 4; Aug: 4; Oct: 4; Dec: 4 | 20
2 | Attend Staff meetings | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 52
3 | Attend Council Meetings | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
6 | Write and achieve approved Policies how to handle emergencies, requirements for volunteers, etc. | July: 4; Aug: 4; Sept: 2 | 10
4 | Develop, plan and execute Intergenerational events and other special events (Christmas Program, etc.) | Mar: 4; Sept: 4; Nov: 2; Dec: 4 | 14
TOTAL |  | 37 | 38 | 61 | 38 | 38 | 171 | 184 | 203 | 39 | 31 | 29 | 39 | 908
| Possible Hours at 20/week | 80 | 80 | 100 | 80 | 80 | 100 | 80 | 80 | 100 | 80 | 80 | 100 | 1040