## By Category
RezFest ToDo's
Overall |  | Lead days | Completed
- | Determine events | 180 | X
- | Design graphics | 90 | X
- | Get Fire Truck demo | 30
- | Get Police K9 demo | 30
Car, Truck & Bike Show |  | Lead days | Completed
- | Design Flyer | 120 | X
- | Determine traffic and parking | 120
- | Determine signage needs | 120
- | Print Flyers | 90 | X
- | Design Online Graphics | 90 | X
- | Design Car Cards | 90 | X
- | Solicit donations | 90
- | Handout Flyers | 30
- | Deploy Online Graphics | 30 | X
- | Get Trophies | 30
- | Make required signs | 30
- | Secure staffing | 14
- | Print Car cards | 7
- | Make & pack goodie bags | 7
- | Mark parking spots | 3
- | Set up registration booth | 0
- | Place signage | 0
Music |  | Lead days | Completed
- | Book Bands - 3 month lead | 90 | X
- | Get stage layouts | 30
- | Get promo info from bands | 45
- | Add to general flyers and graphics | 45
- | Determine power needs | 30
- | Build Stage
Food Trucks and Drinks |  | Lead days | Completed
- | Determine desired trucks | 120 | X
- | Determin drinks needs | 120 | X
- | Book trucks | 90
- | Get insurance and permit docs | 90
- | Determine parking placement | 60
- | Verify bookings | 14
Kids Activities |  | Lead days | Completed
- | Determine Games | 120
- | Decide on prizes | 90
- | Determine Bouncies | 60
- | Book Bouncies | 60
- | Secure prizes | 30
- | Secure Staffing | 14
Community Service Tables |  | Lead days | Completed
- | Solicit Services | 120
- | Secure staffing | 14
- | Help Setup | 0
- | Cleanup | 0
Vendor Tables |  | Lead days | Completed
- | Solicit Vendors | 120
- | Secure staffing | 14
- | Help Setup | 0
- | Cleanup | 0
Tents & Chairs & Tables |  | Lead days | Completed
- | Determine Tent & chair & table needs | 120
- | Book tent & chairs & tables | 60
- | Determine Staffing | 14
- | Supervise tent setup | 3
- | Setup Chairs & tables | 3
- | Clean Tables & chairs | 0
Raffle |  | Lead days | Completed
- | Determine Raffle((s) | 120
- | Secure ticket Drum | 60
- | Determine Timing | 30
- | Secure Staffing | 14
- | Get tickets | 14
- | Get ticket drum | 7
- | Sell tickets | 0
Power |  | Lead days | Completed
Sound |  | Lead days | Completed
Medical Table |  | Lead days | Completed
Security |  | Lead days | Completed
Communication |  | Lead days | Completed
Inside |  | Lead days | Completed
Setup |  | Lead days | Completed
Takedown |  | Lead days | Completed
Sponsor Solicitation |  | Lead days | Completed

## By Lead Days
RezFest ToDo's
Category | Task | Lead days | Completed
Overall | Determine events | 180 | X
Car, Truck & Bike Show | Design Flyer | 120 | X
Car, Truck & Bike Show | Determine traffic and parking | 120
Car, Truck & Bike Show | Determine signage needs | 120
Food Trucks and Drinks | Determine desired trucks | 120 | X
Food Trucks and Drinks | Determin drinks needs | 120 | X
Kids Activities | Determine Games | 120
Community Service Tables | Solicit Services | 120
Vendor Tables | Solicit Vendors | 120
Tents & Chairs & Tables | Determine Tent & chair & table needs | 120
Raffle | Determine Raffle((s) | 120
Overall | Design graphics | 90 | X
Car, Truck & Bike Show | Print Flyers | 90 | X
Car, Truck & Bike Show | Design Online Graphics | 90 | X
Car, Truck & Bike Show | Design Car Cards | 90 | X
Car, Truck & Bike Show | Solicit donations | 90
Music | Book Bands - 3 month lead | 90 | X
Food Trucks and Drinks | Book trucks | 90
Food Trucks and Drinks | Get insurance and permit docs | 90
Kids Activities | Decide on prizes | 90
Food Trucks and Drinks | Determine parking placement | 60
Kids Activities | Determine Bouncies | 60
Kids Activities | Book Bouncies | 60
Tents & Chairs & Tables | Book tent & chairs & tables | 60
Raffle | Secure ticket Drum | 60
Music | Get promo info from bands | 45
Music | Add to general flyers and graphics | 45
Overall | Get Fire Truck demo | 30
Overall | Get Police K9 demo | 30
Car, Truck & Bike Show | Handout Flyers | 30
Car, Truck & Bike Show | Deploy Online Graphics | 30 | X
Car, Truck & Bike Show | Get Trophies | 30
Car, Truck & Bike Show | Make required signs | 30
Music | Get stage layouts | 30
Music | Determine power needs | 30
Kids Activities | Secure prizes | 30
Raffle | Determine Timing | 30
Car, Truck & Bike Show | Secure staffing | 14
Food Trucks and Drinks | Verify bookings | 14
Kids Activities | Secure Staffing | 14
Community Service Tables | Secure staffing | 14
Vendor Tables | Secure staffing | 14
Tents & Chairs & Tables | Determine Staffing | 14
Raffle | Secure Staffing | 14
Raffle | Get tickets | 14
Car, Truck & Bike Show | Print Car cards | 7
Car, Truck & Bike Show | Make & pack goodie bags | 7
Music | Build Stage | 7
Raffle | Get ticket drum | 7
Car, Truck & Bike Show | Mark parking spots | 3
Tents & Chairs & Tables | Supervise tent setup | 3
Tents & Chairs & Tables | Setup Chairs & tables | 3
Car, Truck & Bike Show | Set up registration booth | 0
Car, Truck & Bike Show | Place signage | 0
Community Service Tables | Help Setup | 0
Community Service Tables | Cleanup | 0
Vendor Tables | Help Setup | 0
Vendor Tables | Cleanup | 0
Tents & Chairs & Tables | Clean Tables & chairs | 0
Raffle | Sell tickets | 0